## Task Plan
Task ID | Sprint | Week | Role | Assigned to (name) | Task (one PR) | Due (sprint day) | Status | PR link | Notes
S1-DEV-01 | 1 | 1 | Developer | Ivan Abduhadi | Project scaffold: app skeleton, env config, DB connection | 2 | Not started
S1-DEV-02 | 1 | 1 | Developer | Ivan Abduhadi | Register user form and API (new users start as pending) | 4 | Not started
S1-DEV-03 | 1 | 1 | Developer | Ivan Abduhadi | Login and logout with session handling | 5 | Not started
S1-DEV-04 | 1 | 2 | Developer | Ivan Abduhadi | Password hashing and set-password on first login | 6 | Not started
S1-DEV-05 | 1 | 2 | Developer | Ivan Abduhadi | Reset password: request, emailed token, reset form | 7 | Not started
S1-DEV-06 | 1 | 2 | Developer | Ivan Abduhadi | Superadmin: approve pending users and designate admins; block removing or disabling the last remaining superadmin | 8 | Not started
S1-DEV-07 | 1 | 2 | Developer | Ivan Abduhadi | Admin/superadmin: assign per-module rights (view, edit, delete); log every rights change in audit_log | 9 | Not started
S1-DEV-08 | 1 | 2 | Developer | Ivan Abduhadi | Main page: module tiles by view right, plus server-side permission check | 9 | Not started
S1-DBA-01 | 1 | 1 | DB Admin | Keith Marlou Aldueza | Team database setup, migration runner script, and student setup README (no Docker) | 2 | Not started
S1-DBA-02 | 1 | 1 | DB Admin | Keith Marlou Aldueza | Migration: HOPE base tables and sample data from HopeDB_audit.sql | 3 | Not started
S1-DBA-03 | 1 | 1 | DB Admin | Keith Marlou Aldueza | Migration: app_user, role, module, user_permission (with soft delete) | 4 | Not started
S1-DBA-04 | 1 | 1 | DB Admin | Keith Marlou Aldueza | Migration: password reset token table (hashed, expiry, used flag) | 5 | Not started
S1-DBA-05 | 1 | 1 | DB Admin | Keith Marlou Aldueza | Seed data: one superadmin account per team member, 4 modules, default roles (no passwords in the repo; first password set via one-time set-password link) | 5 | Not started
S1-DBA-06 | 1 | 2 | DB Admin | Keith Marlou Aldueza | Make audit_user() record the logged-in user in audit_log; test it | 8 | Not started
S1-TST-01 | 1 | 1 | Tester | Ivan Abduhadi | Sprint 1 test plan and acceptance criteria | 3 | Not started
S1-TST-02 | 1 | 1 | Tester | Ivan Abduhadi | Test cases: register and login | 5 | Not started
S1-TST-03 | 1 | 2 | Tester | Ivan Abduhadi | Test cases: set and reset password (expired and reused token) | 7 | Not started
S1-TST-04 | 1 | 2 | Tester | Ivan Abduhadi | Permission matrix tests (superadmin/admin/user x view/edit/delete), using registered and approved test accounts for admin and user | 9 | Not started
S1-TST-05 | 1 | 2 | Tester | Ivan Abduhadi | Automated smoke test: login and main page | 9 | Not started
S1-TST-06 | 1 | 2 | Tester | Ivan Abduhadi | Bug reports and fix verification | 9 | Not started
S1-UIX-01 | 1 | 1 | UI/UX Designer | Nathaniel Ashley Ellacer | Design system: colors, typography, core components | 2 | Not started
S1-UIX-02 | 1 | 1 | UI/UX Designer | Nathaniel Ashley Ellacer | Wireframes: login, register, set/reset password | 3 | Not started
S1-UIX-03 | 1 | 1 | UI/UX Designer | Nathaniel Ashley Ellacer | Wireframes: main page and user-rights management | 4 | Not started
S1-UIX-04 | 1 | 2 | UI/UX Designer | Nathaniel Ashley Ellacer | Hi-fi mockups and developer handoff notes | 6 | Not started
S1-UIX-05 | 1 | 2 | UI/UX Designer | Nathaniel Ashley Ellacer | Usability review of built screens and fix list | 9 | Not started
S1-SM-01 | 1 | 1 | Scrum Master | John Patrick Narvasa | Repo setup: branch protection, PR and issue templates | 1 | Not started
S1-SM-02 | 1 | 1 | Scrum Master | John Patrick Narvasa | Sprint 1 board: stories with acceptance criteria | 1 | Not started
S1-SM-03 | 1 | 1 | Scrum Master | John Patrick Narvasa | Team working agreement, Definition of Done, role guide | 2 | Not started
S1-SM-04 | 1 | 1 | Scrum Master | John Patrick Narvasa | Mid-sprint check notes and impediment log | 5 | Not started
S1-SM-05 | 1 | 2 | Scrum Master | John Patrick Narvasa | Sprint 1 review and retrospective report | 10 | Not started
S2-DEV-01 | 2 | 3 | Developer | Ivan Abduhadi | Customer list with search and filter (permission-checked) | 2 | Not started
S2-DEV-02 | 2 | 3 | Developer | Ivan Abduhadi | Customer create and edit form | 3 | Not started
S2-DEV-03 | 2 | 3 | Developer | Ivan Abduhadi | Customer soft delete and restore | 4 | Not started
S2-DEV-04 | 2 | 3 | Developer | Ivan Abduhadi | Product list with search and filter | 5 | Not started
S2-DEV-05 | 2 | 4 | Developer | Ivan Abduhadi | Product create and edit form | 6 | Not started
S2-DEV-06 | 2 | 4 | Developer | Ivan Abduhadi | Product soft delete and restore | 7 | Not started
S2-DEV-07 | 2 | 4 | Developer | Ivan Abduhadi | Price history: add price with effective date | 8 | Not started
S2-DEV-08 | 2 | 4 | Developer | Ivan Abduhadi | Current-price display on product page; permission checks across both modules | 9 | Not started
S2-DBA-01 | 2 | 3 | DB Admin | Keith Marlou Aldueza | Customer and product active views, indexes | 2 | Not started
S2-DBA-02 | 2 | 3 | DB Admin | Keith Marlou Aldueza | Query: current price as of a given date | 4 | Not started
S2-DBA-03 | 2 | 3 | DB Admin | Keith Marlou Aldueza | Validation constraints (payTerms, unit) | 5 | Not started
S2-DBA-04 | 2 | 4 | DB Admin | Keith Marlou Aldueza | Verify child-record delete checks for customer and product | 6 | Not started
S2-DBA-05 | 2 | 4 | DB Admin | Keith Marlou Aldueza | Demo data for customer, product, price history | 7 | Not started
S2-DBA-06 | 2 | 4 | DB Admin | Keith Marlou Aldueza | Search performance check and index tuning | 9 | Not started
S2-TST-01 | 2 | 3 | Tester | Ivan Abduhadi | Test cases: customer module | 3 | Not started
S2-TST-02 | 2 | 3 | Tester | Ivan Abduhadi | Test cases: product and price history | 5 | Not started
S2-TST-03 | 2 | 4 | Tester | Ivan Abduhadi | Soft delete/restore tests, incl. delete blocked by active children | 7 | Not started
S2-TST-04 | 2 | 4 | Tester | Ivan Abduhadi | Permission tests per module | 8 | Not started
S2-TST-05 | 2 | 4 | Tester | Ivan Abduhadi | Regression test of Sprint 1 | 9 | Not started
S2-TST-06 | 2 | 4 | Tester | Ivan Abduhadi | Bug reports and fix verification | 9 | Not started
S2-UIX-01 | 2 | 3 | UI/UX Designer | Nathaniel Ashley Ellacer | Wireframes: customer screens | 2 | Not started
S2-UIX-02 | 2 | 3 | UI/UX Designer | Nathaniel Ashley Ellacer | Wireframes: product and price history screens | 3 | Not started
S2-UIX-03 | 2 | 3 | UI/UX Designer | Nathaniel Ashley Ellacer | Hi-fi mockups and handoff notes | 5 | Not started
S2-UIX-04 | 2 | 4 | UI/UX Designer | Nathaniel Ashley Ellacer | Empty, error and confirm-delete states | 7 | Not started
S2-UIX-05 | 2 | 4 | UI/UX Designer | Nathaniel Ashley Ellacer | Usability review of built screens | 9 | Not started
S2-SM-01 | 2 | 3 | Scrum Master | John Patrick Narvasa | Sprint 2 planning notes and board | 1 | Not started
S2-SM-02 | 2 | 3 | Scrum Master | John Patrick Narvasa | Follow up Sprint 1 retro actions | 3 | Not started
S2-SM-03 | 2 | 3 | Scrum Master | John Patrick Narvasa | Mid-sprint check and impediment log | 5 | Not started
S2-SM-04 | 2 | 4 | Scrum Master | John Patrick Narvasa | Update velocity and burndown | 8 | Not started
S2-SM-05 | 2 | 4 | Scrum Master | John Patrick Narvasa | Sprint 2 review and retrospective report | 10 | Not started
S3-DEV-01 | 3 | 5 | Developer | Ivan Abduhadi | Department list and CRUD | 2 | Not started
S3-DEV-02 | 3 | 5 | Developer | Ivan Abduhadi | Job list and CRUD | 3 | Not started
S3-DEV-03 | 3 | 5 | Developer | Ivan Abduhadi | Employee list with search and filter | 4 | Not started
S3-DEV-04 | 3 | 5 | Developer | Ivan Abduhadi | Employee create and edit form | 5 | Not started
S3-DEV-05 | 3 | 6 | Developer | Ivan Abduhadi | Employee soft delete/restore and separation date | 6 | Not started
S3-DEV-06 | 3 | 6 | Developer | Ivan Abduhadi | Job history: add promotion or transfer (effective date, salary) | 7 | Not started
S3-DEV-07 | 3 | 6 | Developer | Ivan Abduhadi | Employee profile with job timeline | 8 | Not started
S3-DEV-08 | 3 | 6 | Developer | Ivan Abduhadi | Restrict salary visibility by permission | 9 | Not started
S3-DBA-01 | 3 | 5 | DB Admin | Keith Marlou Aldueza | Views/queries: employee current job and department | 2 | Not started
S3-DBA-02 | 3 | 5 | DB Admin | Keith Marlou Aldueza | Job history validation (no duplicate effective dates) | 4 | Not started
S3-DBA-03 | 3 | 5 | DB Admin | Keith Marlou Aldueza | Link app_user.empno to employee | 5 | Not started
S3-DBA-04 | 3 | 6 | DB Admin | Keith Marlou Aldueza | Verify child-record delete checks for employee, department, job | 6 | Not started
S3-DBA-05 | 3 | 6 | DB Admin | Keith Marlou Aldueza | HR demo data | 7 | Not started
S3-DBA-06 | 3 | 6 | DB Admin | Keith Marlou Aldueza | Indexes and backup/restore script | 9 | Not started
S3-TST-01 | 3 | 5 | Tester | Ivan Abduhadi | Test cases: department and job | 3 | Not started
S3-TST-02 | 3 | 5 | Tester | Ivan Abduhadi | Test cases: employee | 5 | Not started
S3-TST-03 | 3 | 6 | Tester | Ivan Abduhadi | Job history tests (effective date, salary) | 7 | Not started
S3-TST-04 | 3 | 6 | Tester | Ivan Abduhadi | Salary visibility and permission tests | 8 | Not started
S3-TST-05 | 3 | 6 | Tester | Ivan Abduhadi | Regression test of Sprints 1-2 | 9 | Not started
S3-TST-06 | 3 | 6 | Tester | Ivan Abduhadi | Bug reports and fix verification | 9 | Not started
S3-UIX-01 | 3 | 5 | UI/UX Designer | Nathaniel Ashley Ellacer | Wireframes: department and job screens | 2 | Not started
S3-UIX-02 | 3 | 5 | UI/UX Designer | Nathaniel Ashley Ellacer | Wireframes: employee and profile screens | 3 | Not started
S3-UIX-03 | 3 | 5 | UI/UX Designer | Nathaniel Ashley Ellacer | Job timeline component design | 4 | Not started
S3-UIX-04 | 3 | 5 | UI/UX Designer | Nathaniel Ashley Ellacer | Hi-fi mockups and handoff notes | 5 | Not started
S3-UIX-05 | 3 | 6 | UI/UX Designer | Nathaniel Ashley Ellacer | Usability review of built screens | 9 | Not started
S3-SM-01 | 3 | 5 | Scrum Master | John Patrick Narvasa | Sprint 3 planning notes and board | 1 | Not started
S3-SM-02 | 3 | 5 | Scrum Master | John Patrick Narvasa | Re-prioritize any Sprint 2 carryover | 3 | Not started
S3-SM-03 | 3 | 5 | Scrum Master | John Patrick Narvasa | Mid-sprint check and impediment log | 5 | Not started
S3-SM-04 | 3 | 6 | Scrum Master | John Patrick Narvasa | Update velocity and Sprint 4 risk register | 8 | Not started
S3-SM-05 | 3 | 6 | Scrum Master | John Patrick Narvasa | Sprint 3 review and retrospective report | 10 | Not started
S4-DEV-01 | 4 | 7 | Developer | Ivan Abduhadi | Sales list with search | 2 | Not started
S4-DEV-02 | 4 | 7 | Developer | Ivan Abduhadi | Create sales transaction (customer, salesperson, date) | 3 | Not started
S4-DEV-03 | 4 | 7 | Developer | Ivan Abduhadi | Add line items (product, quantity) | 4 | Not started
S4-DEV-04 | 4 | 7 | Developer | Ivan Abduhadi | Auto-fill unit price from price history as of sales date | 5 | Not started
S4-DEV-05 | 4 | 8 | Developer | Ivan Abduhadi | Record payment against a transaction | 6 | Not started
S4-DEV-06 | 4 | 8 | Developer | Ivan Abduhadi | Balance view per transaction and customer | 7 | Not started
S4-DEV-07 | 4 | 8 | Developer | Ivan Abduhadi | Sales summary report | 8 | Not started
S4-DEV-08 | 4 | 8 | Developer | Ivan Abduhadi | Audit log viewer for superadmin | 9 | Not started
S4-DBA-01 | 4 | 7 | DB Admin | Keith Marlou Aldueza | Query: sales totals and line amounts | 2 | Not started
S4-DBA-02 | 4 | 7 | DB Admin | Keith Marlou Aldueza | Payment balance view | 4 | Not started
S4-DBA-03 | 4 | 7 | DB Admin | Keith Marlou Aldueza | Report queries | 5 | Not started
S4-DBA-04 | 4 | 8 | DB Admin | Keith Marlou Aldueza | Audit log query with filters | 6 | Not started
S4-DBA-05 | 4 | 8 | DB Admin | Keith Marlou Aldueza | Verify delete rules for sales with details or payments | 7 | Not started
S4-DBA-06 | 4 | 8 | DB Admin | Keith Marlou Aldueza | Final DB review: rebuild from migrations, backup, docs | 9 | Not started
S4-TST-01 | 4 | 7 | Tester | Ivan Abduhadi | Test cases: sales transaction | 3 | Not started
S4-TST-02 | 4 | 7 | Tester | Ivan Abduhadi | Price-as-of-date tests | 5 | Not started
S4-TST-03 | 4 | 8 | Tester | Ivan Abduhadi | Payment and balance tests | 7 | Not started
S4-TST-04 | 4 | 8 | Tester | Ivan Abduhadi | End-to-end test: register, approve, login, sell, pay | 8 | Not started
S4-TST-05 | 4 | 8 | Tester | Ivan Abduhadi | Full regression across all modules | 9 | Not started
S4-TST-06 | 4 | 8 | Tester | Ivan Abduhadi | Final test sign-off report | 9 | Not started
S4-UIX-01 | 4 | 7 | UI/UX Designer | Nathaniel Ashley Ellacer | Wireframes: sales entry and line items | 2 | Not started
S4-UIX-02 | 4 | 7 | UI/UX Designer | Nathaniel Ashley Ellacer | Wireframes: payment and balance screens | 3 | Not started
S4-UIX-03 | 4 | 7 | UI/UX Designer | Nathaniel Ashley Ellacer | Report and audit-viewer design | 4 | Not started
S4-UIX-04 | 4 | 7 | UI/UX Designer | Nathaniel Ashley Ellacer | Hi-fi mockups and handoff notes | 5 | Not started
S4-UIX-05 | 4 | 8 | UI/UX Designer | Nathaniel Ashley Ellacer | Final UI consistency and usability pass | 9 | Not started
S4-SM-01 | 4 | 7 | Scrum Master | John Patrick Narvasa | Sprint 4 planning notes and board | 1 | Not started
S4-SM-02 | 4 | 7 | Scrum Master | John Patrick Narvasa | Mid-sprint check and impediment log | 5 | Not started
S4-SM-03 | 4 | 8 | Scrum Master | John Patrick Narvasa | Release checklist and demo script | 8 | Not started
S4-SM-04 | 4 | 8 | Scrum Master | John Patrick Narvasa | Collect final peer evaluations | 9 | Not started
S4-SM-05 | 4 | 8 | Scrum Master | John Patrick Narvasa | Final review, retrospective and project report | 10 | Not started